Town of Mendon

Climate Smart Communities Task Force

12–18 Month Action Plan Overview

PHASE 1: STABILIZE (February – March)

- Goal: Establish structure, direction, and early momentum.

- Tasks

Confirm membership & roles

Adopt mission & guiding principles

Conduct Bronze vs. Impact decision pathway

Seek Town Board strategic endorsement

- Outcome: Clear identity + agreed strategic direction

PHASE 2: SELECT (February – April)

- Goal: Choose priority activities aligned with chosen pathway.

- Tasks

Review CSC checklist

Identify completed / partial / unknown actions

Coordinate with Town departments

Apply prioritization rubric

Select Top 10 priority activities

  - 3–5 Quick Wins

  - 3–5 Medium Effort

  - 1–2 Higher Impact

- Outcome: Preliminary CSC Activity Status & Priority Matrix

PHASE 3: PLAN (April – May)

- Goal: Convert priorities into executable plan.

- Tasks: For each selected activity:

Assign lead & clarify roles

Define what “complete” means

Set timeline & milestones

Identify resources & grant opportunities

Conduct risk & capacity check

- Outcome: Written 12–18 Month Implementation Plan

PHASE 4: IMPLEMENT (Months 6–18)

Goal: Execute with accountability and sustainability.

Tasks

Activate approved activities

Monitor progress at each meeting

Document CSC credit (if applicable)

Provide quarterly Board updates

Conduct biannual capacity check

Outcomes:

- Measurable progress

- CSC points submitted (if applicable)

- Community resilience impact

- Repeatable execution rhythm