Town of Mendon

Climate Smart Communities Task Force

Draft Action Plan

February 2026

## I. Mission Statement

Mission:
The Mendon Climate Smart Communities Task Force advances practical, community-centered actions that strengthen Mendon’s resilience to climate impacts, protect our natural resources, support fiscal responsibility, and position the Town as a responsible steward for future generations.

We serve as a coordinating body that:

- Recommends strategic climate- or sustainability-related actions to the Town Board

- Connects departments, volunteers, and partners to advance actions

- Helps Mendon access state recognition and funding opportunities

- Ensures climate efforts align with Mendon’s character and community priorities

## II. Guiding Principles

- Community First – Focus on actions that matter to Mendon residents.

- Practical & Achievable – Match ambition to capacity.

- Leverage Existing Work – Seek credit for work already completed.

- Act as Coordinators – Coordinate and catalyze; avoid duplicating Town staff roles or Village efforts.

- Resilience-Oriented – Prioritize climate adaptation and vulnerability reduction.

- Strategic Use of CSC Certification – Use Bronze certification as a tool, not the sole purpose.

## III. Confirm Task Force Roles and Responsibilities: Coordinator Model

The Task Force will:

- Identify priorities

- Map who already has authority

- Make formal recommendations

- Assist with grant identification

- Coordinate stakeholders

- Submit documentation to NYS

The Task Force will NOT:

- Duplicate staff work

- Take on operational responsibilities without Board authorization

- Overextend beyond volunteer capacity

## IV. Current Context

- Nine voting members authorized and one ex officio, non-voting HFL high school student[1]

- Several meetings held; organization and direction still forming.

- Strategic tension between:

  - Fast-track Bronze certification

  - Community-priority resilience work

- Decision made not to prioritize PE2 (GHG Inventory) at this time.

- Chair proposes beginning with identifying checklist items already completed.

  - This was solidified through resolution in October 2025.

## V. 12-18 Month Action Plan

## Task 1: Stabilize (February - March)

Objective: Build structure, clarify direction, and secure early momentum.

Step 1.1. Confirm Organizational Structure

- Identify plan to fill remaining 2 seats plus high-school student

- Adopt:

  - Mission statement

  - Guiding principles

- Assign informal roles:

  - Checklist Coordinator (TBD)

  - Note Taker (Rebecca Kreuzer)

  - Resilience/Vulnerability Lead (Tim Engstrom)

  - Communications Lead (Peter Carosa)

  - Village Liaison (TBD)

  - Others?

Step 1.2.  Strategic Alignment: Bronze Certification Decision Pathway

Objective: Decide what kind of task force we want to be.

Decision Pathway Framework

The Task Force will consider the following:

- Capacity Assessment

  - How many active working members?

  - Estimated volunteer hours per month?

  - What level of staff support exists?

  - Is grant writing capacity available?

- Strategic Choice

| Pathway A: Bronze Certification First | Pathway B: Community Impact First | Hybrid Path: Parallel Track |
| --- | --- | --- |
| Focus on fastest checklist completion | Focus on greatest local vulnerabilities | Capture easy points while launching 1–2 meaningful resilience initiatives |
| Clear measurable endpoint | Stronger local impact | Balanced approach |

- Board Alignment Opportunity
Present recommendation to Town Board for strategic endorsement.

# Task 2: Activity Selection (February - March)

### Objective

Translate the strategic direction established in Task 1 into a focused, prioritized set of activities that align with the Task Force’s chosen pathway (Certification-Oriented, Impact-Oriented, or Hybrid).

### Core Question

Given our chosen strategy in Task 1, which specific CSC checklist activities best advance our goals while matching our capacity?

## Output: Preliminary CSC Activity Status & Priority Matrix

This matrix will:

- Categorize all relevant CSC checklist items by status

- Identify documentation needs and/or gaps

- Assess level of effort

- Rank activities based on strategic alignment and feasibility

- Identify recommended priority actions

## Step 2.1 - Checklist Review & Status Mapping (In Progress)

Conduct a structured review of the full CSC checklist and categorize each relevant action as:

- Likely completed (documentation required)

- Partially completed (gaps identified)

- Not completed

- Unknown status

For each item, identify:

- Documentation required

- Existing documentation location (if known)

- Responsible Town department or official

- Estimated effort to complete (Low / Medium / High)

Note: If the Task Force has chosen an Impact-First pathway, priority review may focus on adaptation/resilience categories rather than the full checklist.

## Step 2.2: Department & Institutional Coordination

Meet with and/or request input from relevant Town officials or employees:

- Current and/or former Highway Superintendent

- Current and/or former Code Enforcement Officer

- Town Assessor

- Town Clerk

- Emergency Management personnel

- Planning Board or Zoning representatives (as relevant)

Purpose:

- Confirm status of suspected completed activities

- Identify existing policies or plans eligible for CSC credit

- Understand operational realities and implementation capacity

- Avoid duplicating staff efforts

This step reinforces the Task Force’s role as coordinator and conductor, not implementer of record.

## Step 2.3: Prioritization Framework (March)

Using the information gathered, rank activities using the following criteria:

### A. Strategic Alignment

- Does this activity align with our chosen pathway?

- Does it address Mendon’s identified climate vulnerabilities?

- Does it support Town Board priorities?

B. Feasibility

- Level of effort required

- Documentation complexity

- Staff or volunteer capacity needed

- Cost implications

C. Certification Value (if applicable)

- Point value

- Contribution toward Bronze milestone

Step 2.4: Priority Activities Selection (March)

Select:

- Top 10 priority CSC checklist activities, including:

  - 3–5 low-lift or documentation-based actions (quick wins)

  - 3–5 medium-effort actions aligned with community impact

  - 1–2 higher-impact initiatives (if capacity allows)

If pursuing an Impact-First pathway:

- Select 3–5 resilience-focused initiatives even if point accumulation is secondary.

Task 3: Implementation Planning (April - May)

### Objective

Convert selected priority activities into a clear, time-bound execution plan with defined responsibility and accountability.

## Step 3.1 -  Define Ownership

For each priority activity:

- Who is the lead? (Task Force member, Town department, or external partner)

- What is the Task Force role? (Convene, recommend, draft, document, apply, monitor)

- Does the Town Board need to authorize action?

## Step 3.2: Define Scope & Outcome

For each priority activity:

- What does “complete” look like?

- What documentation is required (if CSC credit is involved)?

- What level of Town Board approval is required?

- Is this policy adoption, physical improvement, planning, or reporting?

## Step 3.3: Establish Timeline

For each priority activity, determine:

- Start date

- Key milestones

- Target completion date

## Step 3.4: Identify Resources

- Volunteer time required

- Staff time required

- Any estimated costs

- Grant opportunities (if relevant)

- External expertise needed

If additional resources are needed or unclear, flag for Town Board guidance.

## Step 3.5: Risk & Capacity Check

Before finalizing, ask:

- Are we overcommitting?

- Do timelines overlap unrealistically?

- Are responsibilities unevenly distributed?

- Do we have at least 1–2 “quick wins” to maintain momentum?

## Outcome of Task 3

By completion, the Task Force will have:

- A written implementation plan

- Assigned leads

- Clear deadlines

- A realistic scope aligned with capacity

Task 4: Implementation (12-18 months)

### Objective

Execute the approved Implementation Plan in a structured, accountable, and sustainable manner while maintaining alignment with Town capacity and priorities

## Core Principle

The Task Force serves as a coordinator and catalyst, not the sole implementer.

Implementation may be carried out by:

- Town departments

- Task Force members

- Partner organizations

- Consultants

- Volunteers

The Task Force ensures progress, accountability, and documentation.

## Step 1: Activate Approved Activities

For each activity approved in Task 3:

- Confirm lead responsibility

- Confirm timeline

- Confirm Board authorization (if required)

- Initiate first milestone action

No activity begins without clarity on these four items.

## Step 2: Monitor & Support Progress

At each regular meeting:

- Brief status updates (5 minutes per active activity)

- Identify barriers

- Reallocate support if necessary

- Confirm milestone completion

If an activity stalls:

- Clarify whether the barrier is authority, capacity, funding, or scope.

- Adjust timeline or escalate to the Town Board as appropriate.

Step 3: Documentation & CSC Credit

If certification points are sought:

- Collect required documentation contemporaneously.

- Assign responsibility for submission.

- Track point totals quarterly.

## Step 4: Reporting & Transparency

Quarterly (?):

- Provide a concise written update to the Town Board.

- Update public-facing tracking (if applicable).

- Note wins, challenges, and adjustments.

Annual:

- Summarize accomplishments.

- Evaluate effectiveness.

- Recommend next-year priorities.

Step 5: Capacity Check & Course Correction

Twice annually, ask:

- Are we overcommitted?

- Are timelines realistic?

- Is our strategic pathway (Certification / Impact / Hybrid) still appropriate?

- Do we need to pause, accelerate, or shift?

Adjust deliberately, not reactively.

## VI. CSC Certification Strategy

Proposed strategy:

- Capture low-lift existing credits

- Align resilience projects with CSC point structure where feasible

- Avoid checklist-only activities that do not serve local priorities

## VII. Meeting Structure Reset (to stop circular conversations)

Each meeting agenda should include:

- 10 min – Updates

- 20 min – Specific Action Item

- 20 min – Decision Needed

- 10 min – Assignments & Deadlines

No open-ended philosophical looping unless scheduled intentionally.

## VIII. Immediate Next 3 Meetings Plan

March 2026 Meeting

- Adopt mission and guiding principles

- Decision Pathway for Mission and Focus (Certification, Impact, or Hybrid)

- Review

April 2026 Meeting

- Present checklist findings

- Identify top 10 “likely credit” actions

- Begin vulnerability discussion framework

May 2026 meeting

- Decide Pathway (Bronze-first, Resilience-first, Hybrid)

- Vote on 1–2 focus areas for next 6 months

IX. Success Indicators (Year 1)

- Clear identity and operating rhythm

- 10–20 CSC points submitted (if applicable)

- 1 formal recommendation to Town Board

- 1 resilience project launched or grant submitted

- Stronger coordination across Town departments

Optional Add-On: Decision Matrix Slide for the Board

Axis 1: Speed to Bronze
Axis 2: Community Impact
Axis 3: Volunteer Capacity Required

This reframes the tension as a strategic choice, not a philosophical divide.

[1] As of February 2026, seven members have been appointed with two additional voting members still needed (a Town resident and a Town employee), and one non-voting high-school student.